## comments
comment_type_id | mod_date | add_date | comment_id | comments | property_id | mod_user | grant_id
1010 | 2004-08-19 12:14:59 |  | 112437 | ACCOMPLISHMENTS The Three Rivers Brownfield Redevelopment Authority (TRBRA) held monthly meetings during this reporting period. In addition, the City formed an Economic Development Team (EDT), which consists of the City Manager, Assistant to the City Manager, Special Projects Coordinator, Zoning Administrator/Building Official, and the Chamber of Commerce Director. The EDT continually discusses potential projects. (QR 3, 1/1/02-3/31/02) The TRBRA continues to hold monthly meetings to discuss Brownfields activities. (QR 5, 7/1/02-9/30/02; QR 6, 10/1/02-12/31/02) The TRBRA held monthly meetings during the quarter. (QR 10, 10/1/03-12/31/03) The Quality Assurance Project Plan (QAPP) was reviewed and approved. (QR 3, 1/1/02-3/31/02) The Pilot utilizes existing databases to identify and prioritize Brownfields properties within the area and is continually updating and enhancing the inventory profiles. (QR 5, 7/1/02-9/30/02) Pat Greve, a member of the Brownfields Redevelopment Authority (BRA), made a presentation at the Chamber of Commerce breakfast on October 11, 2002. (August 6, 2002 BRA Meeting Minutes, attached to QR 5, 7/1/02-9/30/02) The Three Rivers BRA staff attended a Brownfields seminar at Michigan State University in October 2002. The seminar introduced new software which would allow easy tracking of tax captures and other brownfields activities. (QR 6, 10/1/02-12/31/02) |  | NFT | 46872444
1010 | 2004-08-19 15:37:50 |  | 109446 | ACCOMPLISHMENTS The Pilot convened a Technical Team. (QR 1, 10/1/00-12/31/00) The technical team consists of representatives of the City of Allegan, Michigan Department of Environmental Quality (MDEQ), USEPA, Allegan Brownfield Redevelopment Authority (ABRA) and AKT Peerless. (QR 2, 1/1/01-3/31/01) A technical advisory meeting was held in April and May 2001. (QR 3, 4/1/01-6/30/01) The Pilot held a Technical Committee meeting on November 15, 2001 to discuss the results of the AKT Peerless file review. (QR 5, 10/1/01-12/31/01) The Pilot held a kick-off meeting on March 16, 2001 that included Law Weathers and Richardson and AKT Peerless Environmental Services in addition to the City of Allegan Redevelopment Authority. (QR 2, 1/1/01-3/31/01) The Pilot finalized the workplan and began the QAPP. (QR 3, 4/1/01-6/30/01) The Pilot contractor, AKT Peerless, completed the QAPP. (QR 4, 7/1/01-9/30/01) The QAPP was reviewed and approved (QR 6, 1/1/02-3/31/02) The Pilot conducted a file review for the Mobil property and is preparing for Phase I assessments for the Depot Hill, Mill District, and Brady Street properties. (QR 7, 4/1/02-6/30/02) The City of Allegan Brownfield Redevelopment Authority (ABRA) held monthly meetings. (QR 8, 7/1/02-9/30/02; QR 9, 10/1/02-12/31/02) ABRA met to discuss and approved the Brady Street Phase II ESA and BEA. (QR 12, 7/1/03-9/30/03) |  | YED | 63944624
1010 | 2004-08-24 20:21:11 |  | 728678 | ACCOMPLISHMENTS The Pilot held three information and orientation sessions in December 1998, at three different locations in the city, all in proximity to one or more brownfield properties. Approximately 90 training candidates attended the information sessions. (QR 1, 10/1/98-12/31/98) A follow-up information session was held on January 6, 1999 during which applications were accepted from potential students. (QR 2, 1/1/99-3/31/99) New Directions proceeded with job placement efforts. New Directions Job Developers worked with trainees to market the group to employers by providing labor market information. (QR 3, 4/1/99-6/30/99) The Pilot continued its outreach efforts through the use of newspaper ads, posters, and flyers. In addition, the Pilot held information sessions at various locations in the brownfields target area. (QR 5-9, 10/1/99-12/31/00) The Pilot reported that the fourth New Bedford Brownfields Environmental Technician Aide Job Training Program began on January 22, 2002. Recruitment activities included group orientations and one-on-one interview sessions to interested applicants. The Pilot conducted the Test for Adult Basic Education (TABE) on applicants to determine which candidates met the academic criteria of the program. (QR 13, 10/1/01-12/31/01) The Pilot implemented a new innovative technology 6-hour course addition to the curriculum, related to Geographic Information Systems (GIS), which is a mapping software capable of overlays utilizing digitized data to identify hazardous waste sites, landfills, wetlands, aquifers, etc. (QR 14, 1/1/02-3/31/02) On November 19, 2002, the Pilot held an all-class reunion. The Pilot was able to contact 28 graduates from 1999-2002, and sixteen showed interest in attending. Highlights of the reunion were when participants shared their success stories and exchanged job leads and employer information. The organizers also offered participants continued support as a clearinghouse for general information, educational information, job placement leads, and re-licensing information. (QR 17, 10/1/02-12/31/02) The Pilot participated in a forum on December 10, 2002, for small to medium size firms to apply for contracts on the New Bedford Harbor Superfund project. The Pilot had a display about the New Bedford job training program. Several graduates were also able to give their resumes to contractors. (QR 17, 10/1/02-12/31/02) The Pilot engaged in outreach and recruitment activities in New Bedford brownfields neighborhoods for the fifth training cycle in November and December 2003. Thirty eight people participated in information sessions. The Pilot also distributed flyers and received free advertising on local television. (QR 17, 10/1/02-12/31/02) Eighty individuals applied for the program. The Pilot conducted the Test for Adult Basic Education (TABE) on applicants to determine which candidates met the academic criteria of the program. (QR 18, 1/1/03-3/31/03) The Pilot reported that the training at Bristol Community College for the fifth training cycle was completed on May 9, 2003, and that the Lead/Asbestos training ran from May 12 to May 22. The Institute for Environmental Education provided the Lead/Asbestos training at the New Directions Business and Industry Center. (QR 19, 4/1/03-6/30/03) The Pilot reported continued efforts to contact environmental employers about job openings, and to provide graduates with support in obtaining employment. The Pilot provides graduates with career counseling, job networks, resume and interview workshops, and job search resources. (QR 21, 10/1/03-12/31/03) The Pilot offerred free re-licensing classes to past graduates. These eight-hour classes were held on Saturdays at the Institute for Environmental Education (IEE). Course names and the number of attendees are listed below: May 1, 2004 - Hazwoper (Refresher): 8 attendees May 8, 2004 - Asbestos (Contractor/Supervisor Refresher): 8 attendees May 15, 2004 - Lead (Contractor/Supervisor Refresher): 6 attendees (QR 23, 4/1/04-6/30/04) |  | NOJ | 57101690
1010 | 2004-08-25 15:26:04 |  | 511799 | PILOT ACCOMPLISHMENTS The Pilot reported that it hosted a public outreach event on November 10, 2003. (QR 5, 10/1/03-12/31/03) The Pilot reported that the brownfields project was presented to the Yankton Historic Riverfront District Board of Directors on February 10, 2004. (QR 6, 1/1/04-3/31/04) The Pilot reported that the brownfields project was the focus of a discussion on the local radio show KYNT, which discussed the history of the project, findings to date, longer development plans, and contact information if people have questions. (QR 6, 1/1/04-3/31/04) The Pilot reported that all of the Pilot-funded Phase I and Phase II assessment reports can be viewed on the city's website, www.cityofyanktonnow.com. (QR 6, 1/1/04-3/31/04) |  | BBC | 43500654
1010 | 2004-08-25 19:11:20 |  | 113046 | ACCOMPLISHMENTS The Pilot has been talking with environmental employers to identify skill needs. Their efforts resulted in the discovery that air and bulk monitoring training would be very useful to Pilot participants. (QR 1, 4/1/02-6/30/02) The Pilot reported that through their partnerships they have been able to offer participants courses in life skills such as, Advanced Attitudinal Training and Budgeting, and to open bank accounts for Pilot graduates that obtained employment (Pilot partner SEED/IMPACT is matching 2-1 every dollar a participant puts in the bank up to $3,000). (QR 1, 4/1/02-6/30/02) The Pilot reported that all participants are invited to participant in evening activities that would enhance their academic and computer skills, as well as budgeting, counseling and other enhancing life skill activities. (QR 2, 7/1/02-9/30/02) The Pilot reported that participants were introduced to Innovative Technologies, such as air sparging, bioremediation, in/ex situ techniques, chemical dehalogention, natural attenuation, soil vapor/washing extraction, solvent extraction, and treatment walls. (QR 1, 4/1/02-6/30/02) The Pilot reported that they have additionally included CPR, math and chemistry hours, Hazardous Communications and First Aid training in their third cycle of classes. (QR 4, 1/1/03-3/31/03) |  | NOJ | 37975214
1010 | 2004-09-02 12:50:13 |  | 654361 | ACCOMPLISHMENTS The following documents relative to the revolving loan fund program were finalized after coordinating the review of the documents with the City of Worcester Law Department: (QR 2, 10/102-12/31/02) 1. A BCRLF eligibility and application requirements fact sheet, including complinace requirements with specific federal regulations. 2. The Loan Fund Application 3. The Loan Fund Promissory Note 4. The Loan Fund Agreement 5. Mortgage and Security Agreement 6. Truth in Lending Disclosure Agreement 7. A Loan Guaranty Agreement The Pilot's representatives attended on-going monthly meetings of the Mayor's Brownfields Roundtable forum to discuss and explain the revolving loan fund program. (QR 2, 10/1/02-12/31/02) The Pilot met with and discussed the loan program with three potential borrowers and also met with officials from MassDevelopment to discuss coordination of the city's revolving loan fund program with specific brownfields loan programs offered by MassDevelopment in order to leverage additional funding for cleanups. (QR 2, 10/1/02-12/31/02) The Pilot completed a brochure that will be used as handouts as well as for a mailing to targeted individuals, property owners and financial institutions to promote the program. (QR 3, 1/1/03-3/31/03) The Pilot coordinated an effort with the Worcester Area Regional Chamber of Commerce to have general brownfields information, including the BCRLF program, published in the Chamber's monthly newsletter and also made the information available on the Chamber's website. (QR 5, 7/1/03-9/30/03) |  | BBC | 42997713
1010 | 2004-09-08 14:50:12 |  | 101815 | ACCOMPLISHMENTS The Pilot has developed a Brownfields Toolbox/Information Guide that provides a comprehensive database of resource names, addresses, and telephone numbers of organizations and companies involved in redevelopment of Brownfields areas and a bibliography to support the database. (AP/SC QR 4, 7/1/99-9/30/99) A glossary and acronyms section for the Brownfields Toolbox has also been created. (AP/SC QR 22, 1/1/04-3/31/04) The Eastward Ho! Brownfields Partnership's GIS Workgroup has adopted a "Conceptual Plan" that provides a roadmap of activities and projects that must be undertaken to build a regional GIS system that will provide information on brownfields to variety of users. Information on the Eastward Ho! Brownfields Partnership, the GIS Workgroup, along with maps and photos of the Model City target area have been included on the South Florida's Regional Planning Council's web site. (AP/SC QR 1, 10/1/98-12/31/98) The Pilot's GIS Workgroup continued work on the GIS system by providing maps available through the web site. New GIS layers were added during the quarter, including solid waste properties, hazardous waste generators, and toxic waste releases. (AP/SC QR 4, 7/1/99-9/30/99) Additional geographic information continued to be collected and added to the database and web site. (AP/SC QR 6, 1/1/00-3/31/00) The web pages can be found at www.sfrpc.com/brnflds.htm. (AP/SC QR 8, 7/1/00-9/30/00) The Pilot reported that the GIS task has been completed and the web site is http://www.sfrpc.com/brwnflds.htm (AP/SC QR 15, 4/1/02-6/30/02) BRIMS website development continued, and preliminary and background information has been posted. (AP/SC QR 22, 1/1/04-3/31/04) The Brownfields Partnership staff is serving on a state-wide technical workgroup that is evaluating a database and geographic information system for brownfields that would be available state-wide and to the public via a web site. (AP/SC QR 10, 1/1/01/3/31/01) An environmental inventory and assessment of an approximately 110-acre area of the Miami River was conducted on October 13-16, 1998. Participants in the inventory included representatives from EPA, Florida Department of Environmental Protection, Miami-Dade County Department of Environmental Resources Management, Miami-Dade County Community Action Agency, City of Miami, and residential and business volunteers from the surveyed area. Results of the inventory will be presented to the Miami River Commission and incorporated into the regional Geographic Information System, which is being created. (AP/SC QR 1, 10/1/98-12/31/98) The Eastward Ho! Brownfields Partnership co-sponsored a public outreach workshop with public and private stakeholders in the Model City area of Miami-Dade County on October 17, 1998. The workshop aimed to inform the residents of the brownfields activities and to determine an area where an environmental inventory and assessment of an approximately 110-acre area within the Model City area will be completed. Approximately 85 people participated in the workshop. (AP/SC QR 1, 10/1/98-12/31/98) The Pilot participated in a number of other community outreach activities in the first quarter including: the Miami River Commission, the Governor's Mission for Sustainable Florida, a brownfields seminar focusing on environmental law, and numerous calls and conferences with area stakeholders. (AP/SC QR 1, 10/1/98-12/31/98) A technical committee of Partnership members has been formed to assist with the task of compiling and analyzing a list of possible properties for Phase I and II assessments in the region. Representatives from Palm Beach, Broward, and Miami-Dade Counties, EPA (South Florida Office), and the Florida Department of Environmental Protection serve on the committee. (AP/SC QR 8, 7/1/00-9/30/00) The Pilot continued to assist the City of Fort Lauderdale to complete the cooperative agreement related paperwork between the U.S. EPA and the City of Fort Lauderdale in establishing their Brownfields Assessment and Demonstration Pilot. The Pilot also assisted the Broward County Brownfields Redevelopment Initiative Task Force (BCBRITF) in an evaluation of their potential Brownfield properties and the City of Fort Myers in developing a public outreach program. (AP/SC QR 4, 7/1/99-9/30/99) The Pilot assisted the BCBRITF with the designation of two properties under the State of Florida Brownfields Program (one in the Hollywood and one in Dania Beach). (AP/SC QR 8, 7/1/00-9/30/00) The Pilot assisted the BCBRITF with the designation of an additional property under the state program for the Liberia area in Hollywood. (AP/SC QR 10, 1/1/01-3/31/01) The Pilot assisted with the designation of a property under the Florida Brownfields Program, the Liberia area in Hollywood. (AP/SC QR 12, 7/1/01-9/30/01) The Pilot continued to assist the BCBRITF with the designation of additional properties in Hollywood, Dania Beach, and Lauderhill. (AP/SC QR 19, 4/1/03-6/30/03; AP/SC QR 20, 7/1/03-9/30/03; AP/SC QR 21, 10/1/03-12/31/03) The Pilot assisted the BCRITF with the designation of additional properties in the State Road 7/441 Corridor, Port Everglades, the cities of Deerfield Beach, Lauderhill, Lauderdale Lakes, Plantation, Miramar, Margate, and Hollywood and unincorporated Broward County. (AP/SC QR 22, 1/1/04-3/31/04) The Pilot assisted the BCBRITF with property designations in the State Road 7/441 Corridor, Hallandale Beach, and unincorporated Broward County. (AP/SC QR 23, 4/1/04-6/30/04) The Pilot provided technical assistance and presentations on the Brownfields program at the monthly meetings of the Miami-Dade Brownfields Oversight Committee, City of Opa-Locka Brownfields Task Force, and the Broward County Brownfields Redevelopment Task Force. The Pilot participated in a meeting of the Miami-Dade County Empowerment Zone on March 12, 1999. The Pilot participated in the quarterly meeting of the Eastward Ho! Brownfields Partnership on January 27 and April 14, 1999. (AP/SC QR 2, 1/1/99-3/30/99; AP/SC QR 3, 4/1/99-6/30/99; AP/SC QR 4, 7/1/99-9/30/99 Brownfields technical assistance were provided to the following: cities of North Miami Beach, Miami, Lake Park, Pompano Beach, Fort Lauderdale, West Palm Beach, Riviera Beach, Opa-Locka, Hollywood, Coconut Creek and Miramar; Miami-Dade, Broward, and Palm Beach Counties; Treasure Coast Regional Planning Council; Florida International University; Hemispheric Center for Environmental Technology; Miami-Dade Community Action Agency; Clark Atlanta University; Miami-Dade Community Action Agency; the Liberia Social and Economic Development Corporation; and the Local Initiatives Support Corporation of Palm Beach County. (AP/SC QR 2, 1/1/99-3/30/99; AP/SC QR 3, 4/1/99-6/30/99; AP/SC QR 4, 7/1/99-9/30/99) The Pilot provided technical assistance on brownfields issues to the following: Miami-Dade Empowerment Zone Trust, Inc.; cities of Del Ray Beach, Miami, Pompano Beach, Fort Lauderdale, West Palm Beach, Opa-Locka, Hollywood, and Deerfield Beach; Miami-Dade, Broward, and Palm Beach Counties; Treasure Coast Regional Planning Council; Florida International University; Hemispheric Center for Environmental Technology; Miami-Dade Community College; Florida Memorial College; Miami-Dade Community Action Agency; and Liberia Social and Economic Development Corporation. (AP/SC QR 8, 7/1/00-9/30/00) The Pilot continued to participate in the local committee and task force meetings and provided technical assistance regarding Brownfields redevelopment projects. (AP/SC QR 18, 1/1/03-3/31/03) The Pilot continued to provide Phase I assessment and technical assistance to the aforementioned communities and non-profits and support other Pilots implement their brownfields programs. (AP/SC QR 19, 4/1/03-6/30/03; AP/SC QR 21, 10/1/03-12/31/03) The Pilot provided assistance to the counties of Miami-Dade, Broward, and Palm Beach counties as well as the cites of Opa-Locka, Miramar, Davie, Plantation, Florida City, Homestead, Pembroke Park, Miami, and North Miami Beach. (AP/SC QR 23, 4/1/04-6/30/04) The Pilot participated in regularly scheduled meetings of the Miami-Dade Brownfields Oversight Committee, City of Opa-Locka Brownfields Task Force, the Broward County Brownfields Redevelopment Task Force, and the newly created City of Pompano Beach Brownfields Citizen Advisory Task Force. (AP/SC QR 6, 1/1/00-3/31/00) In addition to the aforementioned meetings, the Pilot also participated in the meetings of the City of Miami Brownfields Task Force. (AP/SC QR 19, 4/1/03-6/30/03) The Pilot hosted the quarterly meeting of the Eastward Ho! Brownfields Partnership on: January 26, 2000 (AP/SC QR 6, 1/1/00-3/31/00; AP/SC QR 7, 4/1/00-6/30/00); July 26, 2000; (AP/SC QR 8, 7/1/00-9/30/00); August 1, 2001 (AP/SC QR 12, 7/1/01-9/30/01); October 24, 2001 (AP/SC QR 13, 10/1/01-12/31/01); January 28, 2003 (AP/SC QR 18, 1/1/03-3/31/03); and July 23 and April 23, 2003. (AP/SC QR 19, 4/1/03-6/30/03; AP/SC QR 20, 7/1/03-9/30/03) The Pilot provided technical assistance to the Working Group of the Inter-Agency Everglades Ecosystem Restoration Task Force. (AP/SC QR 8, 7/1/00-9/30/00) The Pilot met with representatives of Miami International Airport, Florida DEP, and US EPA (South Florida Office), and the Miami-Dade County Brownfields Oversight Committee to provide technical assistance on developing a Brownfields program for Miami International Airport. The airport is proposed to be divided into nine areas for brownfields assessment and cleanup activities. (AP/SC QR 10, 1/1/01-3/31/01) On March 20, 1999, the first Brownfields Federal Working Group meeting was held at HUD's Florida State Office in Miami. Thus far, 12 people representing eight federal agencies are involved in the working group. (AP/SC QR 2, 1/1/99-3/30/99 Five meetings were held for the coordination of the Brownfields Minority Job Training Program funded by the National Institute of Environmental Health Sciences for targeted areas in Miami-Dade and Broward Counties. Outreach to recruit residents in the targeted areas in Miami-Dade County for the first training class resulted in 145 applicants. Twelve new partners, including the Miami Skill Center, were brought in to provide the program's administrative, programmatic, and in-kind activities. The first training class is scheduled for April 1999. (AP/SC QR 2, 1/1/99-3/30/99) The Pilot participated in the continuing education legal seminar entitled "Environmental and Land Use Law Section of the Florida Bar" on April 23, 1999. On April 9, 1999, the Pilot participated in the seminar, "Opportunities and Challenges in the Empowerment Zone: Removing Environmental Barriers to Urban Redevelopment in Miami-Dade County." On May 17 and 18, 1999, the Pilot participated in the South Florida Restoration Science Forum held in Boca Raton. (AP/SC QR 3, 4/1/99-6/30/99) The Pilot conducted numerous outreach programs including: three meetings in the Model City area to enlist volunteers in working on the inventory and assessment process; participation in the Eastward Ho! Brownfields Minority Job Training Program in Miami-Dade County that graduated the first class on July 22, 1999 and helped the graduates find jobs; developed a public outreach program for Palm Beach County; assisted the City of Pampano Beach in setting up their Brownfields Redevelopment Program; participated in U.S. HUD televised program on Brownfields on September 16, 1999; participated in meetings with the South Florida Urban Resource Partnership; developed a Community Outreach and Education Sub-committee Plan for Miami/Dade County; Assisted EPA's South Florida Office in hosting a panel session that was attended by the EPA Administrator; participated in a workshop on mixed income/mixed use housing opportunities sponsored by the U.S. HUD and South Florida Regional Planning Council; participated in meetings with the Kids Ecology Corps, who have expressed an interest in participating in Brownfields redevelopment activities; participated in a grants writing workshop on July 1, 1999; participated in a meeting on recycling federally controlled properties on September 10, 1999; participated in a Brownfields and Eastward Ho! Partnership Summit with over 85 attendees on September 27-28, 1999; and participated in the 1999 EPA Region 4 Brownfields Project Director's Workshop on August 3-5, 1999. (AP/SC QR 4, 7/1/99-9/30/99) The Pilot provided technical assistance and coordinated with numerous local agencies, federal agencies, state offices, environmental groups, and educational institutions. The Pilot assisted in developing a public outreach plan for Palm Beach County. The Pilot participated in meetings implementing the two Brownfields job training programs. (AP/SC QR 6, 1/1/00-3/31/00; AP/SC QR 7, 4/1/00-6/30/00 The Pilot conducted outreach activities and provided technical assistance on brownfields activities to all communities and local governments in the State Road 7/U.S. Route 144 Corridor in Broward County. This includes 13 municipalities, Broward County, and the Seminole Tribe of Florida. The goal is to designate the entire corridor in Broward County as a brownfields area and to assist in redeveloping the corridor. (AP/SC QR 10, 1/1/01-3/31/01) The Pilot developed informational brochures on the Brownfields program. (AP/SC QR 6, 1/1/00-3/31/00) The Eastward Ho! Brownfields Partnership and the U.S. HUD held a symposium, "Lenders Symposium on Brownfields and Other Environmentally Impaired Properties, Creative Financing: Pathways to a Stronger Deal," on May 3, 2000 in Fort Lauderdale and on May 4, 2000 in Miami. Approximately 95 people attended. (AP/SC QR 7, 4/1/00-6/30/00) The Pilot provided technical assistance to the Hillsborough County Brownfields Assessment and Demonstration Pilot Staff. (AP/SC QR 10, 1/1/01-3/31/01) The pilot continued work on processing the existing list of properties being considered for assessment (Phase I and Phase II) in the region. A Request for Proposal to hire a contractor to undertake the Phase I and Phase II assessment work was drafted and approved by the pilot's legal counsel. The current schedule for the Phase I assessment activities to begin is January 2002. (AP/SC QR 12, 7/1/01-9/30/01) Pilot staff are assisting the cities of Miami, Fort Lauderdale, and Opa-Locka, and the County of Miami-Dade in implementing their Brownfields Assessment and Demonstration pilots by attending regularly scheduled task force meetings and providing technical assistance. The Pilot provided specific technical assistance to 25 local government agencies, regional planning commissions, and education institutions relating to brownfields issues. (AP/SC QR 12, 7/1/01-9/30/01) The Pilot provided technical assistance to 24 local government agencies, commercial establishments, and education institutions relating to brownfields issues. (AP/SC QR 13, 10/1/01-12/31/01) The Pilot provided technical assistance to 28 local government agencies, commercial establishments, and education institutions relating to brownfields issues. (AP/SC QR 21, 10/1/03-12/31/03) The Pilot provided technical assistance to 27 municipalities, counties, and non-profit organizations relating to brownfields issues. (AP/SC QR 22, 1/1/04-3/31/04) The Pilot is coordinating with the South Florida Ecosystem Restoration Task Force which oversees the Everglades Restoration project. The Pilot is implementing Goal 3: Achieve Compatibility of the Built Environment with Ecosystem Restoration and Prservation. (AP/SC QR 18, 1/1/03-3/31/03) The Pilot produced a video on Brownfields redevelopment. It was broadcasted on March 5, 2003, and it demonstrates how local officials can attract private sector investment in Brownfields properties. (AP/SC QR 18, 1/1/03-3/31/03) The Pilot conducted outreach activities during public workshops for the update of the South Florida Regional Planning Council's Strategic Policy Plan on July 22 and August 14, 2003. The Pilot attended: the National Brownfields Showcase Community Committee Research Project Workshop on July 30-August 1, 2003 and the State of Florida Brownfields Conference on August 11-13, 2003. The Pilot assisted the Treasure Coast Regional Planning Council with a brownfields workshop on August 24, 2003. (AP/SC QR 20, 7/1/03-9/30/03 The Pilot continued to assist the municipalities in Miami-Dade County with the designation of additional properties under the Florida Brownfields Program, including cities of Hialeah, Miami, Homestead, Florida City, Opa-Locka, and North Miami Beach. The Pilot also continued to assist municipalities in Palm Beach County with the designation of additional properties under the Florida Brownfields Program, including unincorporated areas of Palm Beach County and the municipalities of West Palm Beach and Lake Worth. Efforts also continued in assisting Miami-Dade County and the cities of Miami, Fort Lauderdale, and Opa-Locka to implement their Brownfields Assessment Pilots. (AP/SC QR 22, 1/1/04-3/31/04) The Pilot continued to assist the municipalities in Miami-Dade County with the designation of additional properties under the Florida Brownfields Program. The Pilot also continued to assist municipalities in Palm Beach County with the designation of additional properties under the Florida Brownfields Program, including unincorporated areas of Palm Beach County and the municipalities of West Palm Beach and Lake Worth. (AP/SC QR 23, 4/1/04-6/30/04) The Pilot made phone calls and held meetings with representatives of the private sector who have expressed interest in participating in brownfields redevelopment. The Pilot also hosted a regional meeting of the Eastward Ho! Brownfields Partnership on January 28, 2004. The Pilot made two presentations on marketing brownfields and regional approaches to brownfields redevelopment at Brownfields 2003, October 27-29, 2003. (AP/SC QR 22, 1/1/04-3/31/04) |  | BBC | 33596749
1010 | 2004-09-14 16:19:45 |  | 109473 | ACCOMPLISHMENTS In July 2000, the St. Louis County Council passed a resolution affirming LCRA's authority to undertake the activities associated with the Wellston BCRLF. (QR 3, 4/1/00-6/30/00) Two additional cities located in St. Louis County invited LCRA to operate within their communities or expand the LCRA's area of operation, which will enhance the Pilot's opportunity to make loans. (QR 10, 1/1/02-3/31/02) LCRA has requested that the Wellston BCRLF be permitted to lend to qualified entities in St. Louis County in areas that LCRA is authorized to operate. The Pilot has received verbal approval from the EPA Project Manager. (QR 4, 7/1/00-9/30/00) St. Louis County Economic Council (CEC) staff has received inquiries from and met with a potential BCRLF borrower for a brownfields redevelopment project elsewhere in St. Louis County. (QR 6, 1/1/01-3/31/01) LCRA staff met with the Department of Health to discuss the LCRA-Department of Health relationship in connection with the Brownfields Site Manager function. The Pilot prepared marketing materials outlining loan policy and a fact sheet. (QR 5, 10/1/00-12/31/00) The Pilot focused on educating the Business Finance corporation board on the Wellston BCRLF program. Officials from several cities located in St. Louis County have inquired about the loan program for sites in their communities. (QR 7, 4/1/01 -6/30/01) During the current quarter, the BCRLF staff worked on marketing materials and outlined policies and procedures for marketing, processing, preparing, and monitoring loan applications. A marketing fact sheet was developed. The staff marketed the Wellson BCRLF with the new marketing materials. Several cities within St Louis County have inquired about the loan program as a result of the marketing efforts. (QR 8, 7/1/01 - 9/30/01) The Pilot reported that they are researching the recent Brownfield legislation in order to understand its impacts. (QR 9, 10/1/01-12/31/01) During this reporting quarter, the Pilot reported that they continue to market the BCRLF program to all communities in St. Louis County, as well as communities with a particular emphasis on the projects for those communities that have only recently authorized the Pilot to operate within their boundaries. The Pilot also continues to assist in the ongoing redevelopment efforts throughout Wellston and other inner ring suburban communities and offer the use of BCRLF funds. In addition, the Pilot continues to research the impacts of recent Brownfields legislation. (QR 11, 4/1/02-6/30/02) The Pilot reported that they are marketing the BCRLF program to a redevelopment effort underway in the inner urban ring suburban community of Jennings. (QR 12, 7/1/102-9/30/02) The Pilot reported that recent activities in redevelopment areas in the unincorporated St. Louis County and municipalities in which LCRA is authorized to operate have included discussions concerning the use of BCRLF funds. (QR 13, 10/1/02-12/31/02) The Community of Marlborough recently authorized LCRA to operate in their community making BCRLF funds available to developers. (QR 14, 1/1/03-1/31/03) LCRA participated in a number of seminars regardind brownfields redevelopment including the availability and use of BCRLF funding. (QR 17, 10/1/03-12/31/03) |  | FFT | 41315097
1010 | 2004-09-16 15:17:02 |  | 112285 | ACCOMPLISHMENTS The Pilot reported that resolutions have been passed by both the City of McKeesport and McKeesport's Redevelopment Authority to sign the Memorandum of Agreement and Contract Service documents. (QR 6, 1/1/02-3/31/02) The Pilot reported that a letter was sent out to the Clairton and Duquesne communities regarding pooling the funds. (QR 12, 7/1/03-9/30/03) The Pilot reported that a letter was distributed regarding coalition forming and roles and responsibilities that need to be filled by agencies. (QR 14, 1/1/04-3/31/04) |  | BBC | 55363628
1010 | 2004-09-17 10:00:53 |  | 100133 | ACCOMPLISHMENTS A Brownfields Taskforce was formed. The members of the taskforce include: staff of the Department of Housing and Community Development, Department of Economic Development, Department of Planning and Zoning, Department of Annexation/Industrial Recruitment and representatives from Economic Development, Charleston County, the Regional Development Alliance, and Four Mile Hibernian Neighborhood Association. The contact representatives are David Rivers, MUSC Biosciences Division and Eric Oltman, Concurrent Technologies Corporation. (QR 2, 1/1/99-3/31/99) The Brownfields Taskforce held its quarterly meeting during December 1999. The topics discussed included: Obtaining a private sector commitment, improving communication between partners, supplemental grant funding, updating the Pilot inventory, and the current real estate market. (QR 5, 10/1/99-12/31/99) A meeting of the Task Force with Howard Kohn of the Chesapeake Group provided a basis for developing a strategic economic development plan for the Enterprise Community. (QR 5, 10/1/99-12/31/99) The Pilot finalized the Strategic Economic Development Plan (SEDP) funded by the Economic Development Administration. The plan recommended a light industrial park with flex space under a planned unit development (PUD). (QR 6, 1/1/00-3/31/00) To ensure ongoing community-based participation, representatives of the Brownfields Project made presentations at neighborhood meetings and distributed the Brownfields video, "A Challenge to American Cities" to a number of local and national organizations. (QR 9, 10/1/00-12/31/00) The Pilot developed a Brownfields Career Development brochure. (QR 9, 10/1/00-12/31/00) The Pilot in partnership with the Medical University of South Carolina's Biosciences Program conducted the Community Leaders Environmental Education Institute. The Institute was designed to provide community leaders with hands on information regarding the redevelopment of Brownfields and the significant role they play in ensuring the success of that redevelopment. The forum also served as the tool by which the city could provide ongoing education and outreach to its citizens. A total of thirty-five neighborhood residents participated. Topics included environmental policy, regulation and protection, issues and strategies for economic development and urban planning, understanding and communicating environmental health issues and public involvement. (QR 15, 4/1/02-6/30/02) The Pilot prepared a website in draft form. The address is http://www.ci.charleston.sc.us/dev/Brownfields_Program/index.html. (QR 16, 7/1/02-9/30/02) The Pilot reported that the website was reconfigured. (QR 23, 4/1/04-6/30/04) A community-wide forum was conducted that enabled the Pilot to share information regarding the Brownfields Pilot Project, the Brownfields Cleanup Revolving Loan Fund and other incentives available to small business. Approximately sixty-five persons were in attendance and included individuals from the legal, real estate and accounting profession. Several small business owners were also in attendance. (QR 16, 7/1/02-9/30/02) The Pilot reported that the inventory of properties was finalized. (QR 23, 4/1/04-6/30/04) |  | BBC | 40253637
1010 | 2004-09-17 16:32:23 |  | 107109 | PILOT ACCOMPLISHMENTS Since the Paterson Plank Road Area is the "backdoor to the busy Meadowlands Sports Complex" and because the area is near several transportation corridors, it has high redevelopment potential. The HMDC has added the Paterson Plank Road Area to its list of redevelopment properties and declared the area "in need of rehabilitation" pursuant to N.G.S.A. 13:17-20 et seq. HMDC has been authorized to prepare a redevelopment plan for the area. (QR 1, 10/1/99 - 12/31/99) The Pilot held the Paterson Plank Road Brownfields Kick-off session on March 10, 2000, and approximately fifty interested parties, property owners, regulators, and students attended. (QR 2, 12/1/99-3/31/00) The Pilot organized a meeting with the mayors of Pilot communities Carlstadt and East Rutherford to meet with representatives from the New Jersey Economic Development Authority and New Jersey Commerce Committee to discuss financial incentives that the towns may want to consider when offering to promote redevelopment within the Brownfields Pilot Project area. The meeting is scheduled for April of 2000. The Pilot held several meeting with private property owners, residents, developers and municipal officials to discuss the future of Paterson Plank Road and the goals of the Pilot. (QR 4, 7/1/00-9/30/00) The Pilot held a meeting with the property owners of the first thirteen properties approved for investigation with Pilot funds on July 19, 2001 and property owners of the additional twenty-nine properties approved for investigation with Pilot funds on September 20, 2001. The meeting afforded the property owners an opportunity to learn more about the Pilot and the environmental assessment process. Subsequent to these meetings, the consultants scheduled individual meetings with several property owners. (QR 8, 7/1/01-9/30/01) The Pilot has sent mailings to and held two meetings for property owners to develop arrangements for property access and the sharing of information. A kick-off session in January 1999 informed property owners, regulators, students, and other interested parties about the goals of the Pilot. (Supplemental Grant Application, 11/21/01) The Pilot drafted an agreement to be used prior to the investigation of privately owned properties. The document will grant the Pilot access to properties and ease the fear of liability on part of the property owner (responsible or not). Specifically, the document provides a level of comfort to the property owner without reducing their responsibility with regard to cleanup obligations needed. (QR 4, 7/1/00-9/30/00) The Pilot completed a community involvement plan. (QR1, 10/1/99-12/31/99) The Pilot developed a revised Community Involvement Plan to enhance stakeholder involvement. (QR 5-7, 10/1/00-6/30/01) The Pilot formed a Technical Work Group comprised of representatives from various federal, state, and local agencies. (QR 1, 10/1/99 - 12/31/99) Three Technical Work Group meetings were held to prioritize properties for assessments. (QR 2, 12/1/99-3/31/00) The Pilot held three technical workgroup meetings to plan the direction of Pilot activities, such as, resource allocation, prioritization of properties for Pilot-funded assessments, and extension of community involvement through use of the Pilot's web site. (QR 3, 4/1/00-6/30/00) The Pilot reported that two Technical Work Group meeting were held. The primary focus of the meeting was to discuss the changing character of the Paterson Plank Road corridor and prepare for the selection of an environmental consultant to conduct environmental investigations. (QR 4, 7/1/00-9/30/00) The Technical Work Group is comprised of mayoral representatives, the HMDC, and advisors from the New Jersey Department of Environmental Protection (NJDEP), the Army Corps of Engineers (ACOE), and the EPA. The group was formed to develop and implement the District's Brownfields program. (Pilot Fact Sheet, May 2001) The Technical Work Group met on October 18 and November 20, 2001. (QR 9, 10/1/01-12/31/01) The technical work group met again on January 9, 2002. In lieu of holding a formal technical work group meeting on March 13, 2002, a summary of the January and February activities was mailed to the group on February 28, 2002. The Pilot reported that the technical work group currently includes representatives of the NJMC, the boroughs of Carlstadt and East Rutherford, the Bergen County Economic Development Corporation, the New Jersey Department of Transportation, and the New Jersey Institute of Technology. Representatives of the EPA and the NJDEP attend the meetings in an advisory capacity. (QR 10, 1/1/02-3/31/02) The Technical Work Group met on April 14, 2003, with nine members in attendance. They discussed the environmental assessment plan and continued work on a redevelopment plan for the study area. They are scheduling a Public Hearing on the redevelopment plan. (QR 15, 4/1/03-6/30/03) The Technical Work Group met on July 10, 2003 with eight members in attendance. A presentation of the draft redevelopment plan for the study area was given and discussed. (QR 16, 7/1/03-9/30/03) The Technical Work Group met on February 20, 2004 to discuss the draft Pilot Case Study and the Summary of Known Environmental Conditions. The Group is making its recommendations to the NJMC regarding future directions for th estudy area, how to apply the brownfields process throughout the Meadowlands District, and how best to inform stakeholders and other interested parties about the Pilot's experiences. Also, on January 23, 2004, the Technical Work Group attended a seminar sponsored by the New Jersey Chapter of the American Planning Association on the recently published guide, "The Redevelopment Handbook". (QR 18, 1/1/04-3/31/04) The Pilot's web site will allow Internet users to obtain information about the Pilot in various forms including text, photographs, and Geographical Information System (GIS) interfaces. The prototype will contain: --Parcel query capability for the PRP study area --Contact Information --News/Events --Brownfields FAQ --Photos --Links to the EPA web site and Brownfields 2000 conference information (QR 2, 12/1/99-3/31/00) The Pilot's web page came online during this quarter. The web site is currently linked to the HMDC homepage (http://www.hmdc.state.nj.us/brownfields/), and soon it will be linked to other Pilot-relevant web sites. (QR 3, 4/1/00-6/30/00) The Pilot reported that several regulators and members of the public have expressed that the web site is a useful tool to learn about the Pilot. (QR 4, 7/1/00-9/30/00) The web site provides a wealth of Pilot-specific information as well as general Brownfields information on the Hackensack Meadowlands District. The web site links to a GIS database that has query capability for the focus area, contact information, news, upcoming events, photos, and links to cooperative partner web sites and Brownfields 2000 conference information. (Pilot Fact Sheet, May 2001) The Pilot reviewed a beta version of the Environmental Law Institute (ELI)'s Brownfields Center web site that includes information regarding the NJMC. The ELI web site will provide a direct link to the NJMC's web site. The web site is a tool for communities and other interested parties across the country to participate in brownfields cleanup and redevelopment. (QR 8, 7/1/01-9/30/01) The Pilot's web site is currently linked to the NJMC Home page at http://www.meadowlands.state.nj.us. The technical work group reviewed a beta version of the new interactive map of the study area at its January 9, 2002 meeting. The map is now live on the Pilot's web site. At the January 9 meeting, the technical work group also reviewed the other pages of the Pilot Web site and made suggestions, particularly with regard to ways the Web site could be used to solicit developer interest. (QR 10, 1/1/02-3/31/02 The Pilot completed property selection activities. The Pilot analyzed each of the 148 properties in the study area using a ranking tool that depicts each property located in the study area and compares it to a number of indicators and databases commonly used to assess the likelihood of contamination [e.g., the Comprehensive Environmental Response, Compensation, and Liability Information System (CERCLIS), NJDEP's Known Contaminated Sites List (KCSL), the Toxics Release Inventory (TRI) reporting requirements, the Emergency Response Notification System (ERNS), registered underground storage tank (UST) listings, leaking UST incident reports, and state hazardous waste site listings). Thirteen of the 148 properties have been selected and targeted for EPA-funded preliminary assessment. The HMDC submitted a request for approval to use Pilot funds to investigate the thirteen properties on June 28, 2001. An additional 16 Pilot properties were selected to potentially undergo preliminary assessment using New Jersey Hazardous Discharge Site Remediation Fund (HDSRF) funds. The Borough of Carlstadt submitted an application to HDRSF requesting assessment funding. (QR 5-7, 10/1/00-6/30/01) An additional twenty-nine properties were approved for EPA for investigation using Pilot funding, resulting in a total of fifty-eight properties covering over sixty-acres that have been identified through the Pilot program as having a high priority need for investigation. (QR 8, 7/1/01-9/30/01) The Borough of Carlstadt received approval of the HDSRF application for preliminary assessment and environmental investigation of 16 Pilot properties. The HDSRF will supplement investigative activities under the Pilot. (QR 9, 10/1/01-12/31/01) The Pilot hosted a meeting on September 28, 2001 with architectural students from Columbia University that included a presentation on the Pilot and taking the students on a tour of the study area. The students are charged with developing design concepts for the redevelopment of the Paterson Plank Road during the fall semester. (QR 8, 7/1/01-9/30/01) The Pilot met with Columbia University architectural students on December 10, 2001. Students presented design concepts for the redevelopment of Paterson Plank Road. (QR 9, 10/1/01-12/31/01) On October 25, 2001, Pilot representatives met with EPA Remediation Project Managers regarding properties included on the National Priorities List that are located within/in the vicinity of the Paterson Plank Road study area. The meeting provided a forum for sharing information to assist with Pilot investigations. (QR 9, 10/1/01-12/31/01) The Pilot attended the annual Brownfields Marketplace in Iselin, New Jersey, in October 2002, where they were able to exchange useful information with other Pilots regarding reuse planning and other activities. (QR 13, 10/1/02-12/31/02) The Pilot, with assistance from the Technical Work Group and H2M Associates, developed an environmental assessement strategy. (QR 13, 10/1/02-12/31/02) A draft summary of known environmental conditions in the study area was completed, including the results of sampling under an area-wide characterization. Pilot staff are compiling these findings for presentation to stakeholders as a Pilot Case Study. (QR 17, 10/1/03-12/31/03 The Pilot approved an agreement with the NJ Institute of Technology who will prepare an inventory of brownfield properties to guide prioritization of these properties for redevelopment. (QR 17, 10/1/03-12/31/03) On January 8, 2004, the Pilot adopted a new Master Plan that places emphasis on redeveloping brownfield and grayfield properties over development of environmentally sensitive areas. (QR 18, 1/1/04-3/31/04) On February 11, 2004, the Pilot attended a seminar on Site Remediation Basics. (QR 18, 1/1/04-3/31/04) The Pilot reported that the technical work group held two meetings, one in April and one in June 2004. (QR 19, 4/1/04-6/30/04) The Pilot prepared a draft of the Case Study of the Paterson Plank Road Area to summarize activities and experiences of the Pilot. The Case Study contains background information on the study area and the Pilot, stakeholder involvement including the Technical Work Group, a brief summary of environmental conditions, redevelopment planning, lessons learned/conclusions, and links to useful web sites. Also, Pilot consultants and NJIT prepared a draft summary of a more technical document describing known environmental conditions. (QR 19, 4/1/04-6/30/04) The Pilot finalized the Case Study of the Paterson Plank Road Area and it was mailed to stakeholders in September 2004. (Final Report QR 20, 7/1/04-9/30/04) A Pilot representative attended Data Day 2004, an outreach effort by the New Jersey Office of Smart Growth to add listings of brownfield properties to the NJ Brownfields Site Mart. The Site Mart is a marketing tool for brownfield properties. (QR 19, 4/1/04-6/30/04) |  | FFT | 63282247